## general_report
Surfbay Customer Care
Displaying 4 issues at 12/Sep/15 11:18 AM.
Project | Key | Summary | Issue Type | Status | Description | Serial | Plot | Model | Further info.
PDI | PDI-214 | PDI to be carried out | PDI (2 weeks) | Done
Swift | SWIFT-8900 | Back wall in shower flexing and bowing | Toilet/Shower (8 Weeks) | Acknowledged | As you look out the big lounge window it's the small window to the right and the right hand curtain. | 017829h | 132 | Soliel | Swift attended w/c 07.09 but return visit required when they will actually resolve issue - date to be confirmed
Good Will | GW-1049 | Vinyl flooring in kitchen has been torn by sharp edge on bottom of freezer when it was moved to access socket behind. | Floor (8 Weeks) | Parts Recieved |  | 017829h | 132 | Soliel | Awaiting on customer
Swift | SWIFT-8588 | Ring has pulled out of curtain | Curtains (8 Weeks) | Engineer Scheduled | As you look out the big lounge window it's the small window to the right and the right hand curtain. | 017829h | 132 | Soliel | Awaiting on Bellfield to confirm attendance
Swift | SWIFT-8589 | Hole appearing in RH cushion. | Lounge Furniture (8 Weeks) | Engineer Scheduled |  | 017829h | 132 | Soliel | Awaiting on Bellfield to confirm attendance
Chargeable Parts | CHARGE-1512 | Price for a coffee table | Chargeable (6 weeks) | Complete | Quote supplied and rejected by customer
Swift | SWIFT-8590 | Corner beading in toilet should be cut in line with the skirting board. | Wallboards/Ceiling Boards (8 Weeks) | Complete | Not a fault, Swift advised as per van spec.
Swift | SWIFT-8272 | One of the sockets behind freezer is not working | Electrical Faults (2 Weeks) | Complete | Surf Bay attended - copy of job sheet attached
Good Will | GW-919 | Exterior door needs re-aligning | Ext Doors & Windows (4 weeks) | Complete | Surf Bay attended - copy of job sheet attached
Swift | SWIFT-8017 | Split in material on upholstery near radiator | Lounge Furniture (8 Weeks) | Complete | Bellfield attended and advised on 05.05.15 - job completed.
Good Will | GW-918 | Door frame to shower is cracked at bottom | Internal Doors (8 Weeks) | Complete | Surf Bay attended - copy of job sheet attached
Good Will | GW-917 | Fitting missing inside shower - end caps | Lounge Furniture (8 Weeks) | Complete | Part only required - despatched to park on 09.06.15.
Generated at Sat Sep 12 11:18:46 BST 2015 by Karen Watson using JIRA 6.2.3#6260-sha1:63ef1d6dac3f4f4d7db4c1effd405ba38ccdc558.